## Sheet1
Copyright © 2020, Dan Rivera, PMP. All Rights Reserved
Risk Register
Risk | Priority | Person Responsible | Mitigation Actions | Criteria to Eliminate
Resources on Vacation | 3 | Daniel Rivera | * Confirm with resources weekly when they will be taking vacation | Vacation tracker is constantly updaed with resource vacation time
Software Integration | 1 | Daniel Rivera | * Identify resources from both internal Tech Company resources and vendor development team * Find out when resources are available from Tech Company, Inc. Security team. * Find out resource availability from PMO Tools Inc, development team. * Set up weekly tech checkpoints until final integration is performed. * Report to business if certain items are not technically feasible. | Both systems are fully integrated and in support status
Foreign Holidays | 4 | Daniel Rivera | * Confirm with project team every month if any foreign holidays. * Confirm with vendor if they have coming holidays for the month | All holidays accounted for
Resource allocation changes | 2 | Daniel Rivera | * Confirm with resource managers every month on resource availability for next month * Update resource plan accordingly * Plan monthly budget accordingly | Budget has been updated to reflect correct resource allocation