## Capital Expense
Copyright © 2020 Dan Rivera, PMP. All Rights Reserved
Account | Budget | Total Budget | YTD Budget | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01
Hardware | Fin Plan | 125000 | 60000 |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 0
| Budget | 60000 | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual | 60000 | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Difference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software | Fin Plan | 300000 | 150000 | 2020-06-01: 150000; 2021-07-01: 150000
| Budget | 300000 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
| Actual | 150000 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Difference | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Contract Service | Fin Plan | 325000 | 150000 | 2020-06-01: 50000; 2020-09-01: 100000; 2020-12-01: 0; 2021-02-01: 100000; 2021-03-01: 50000; 2021-06-01: 0; 2021-07-01: 25000
| Budget | 325000 | 150000 | 0 | 50000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 50000 | 0 | 0 | 0 | 25000
| Actual | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Difference | 275000 | 100000 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 50000 | 0 | 0 | 0 | 25000
Internal Labor | Fin Plan | 250000 | 151470 | 2020-06-01: 24750; 2020-07-01: 21870; 2020-08-01: 19800; 2020-09-01: 20250; 2020-10-01: 21600; 2020-11-01: 21600; 2020-12-01: 21600; 2021-06-01: 98530
| Budget | 243000 | 149400 | 0 | 22680 | 21870 | 19800 | 20250 | 21600 | 21600 | 21600 | 21600 | 21600 | 27000 | 7200 | 7200 | 9000 | 0
| Actual | 22680 | 22680 | 0 | 22680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Difference | 220320 | 126720 | 0 | 0 | 21870 | 19800 | 20250 | 21600 | 21600 | 21600 | 21600 | 21600 | 27000 | 7200 | 7200 | 9000 | 0
CapEx Totals | Fin Plan | 1000000 | 511470 | 0 | 284750 | 21870 | 19800 | 120250 | 21600 | 21600 | 21600 | 0 | 100000 | 50000 | 0 | 0 | 163530 | 175000
| Budget | 928000 | 509400 | 0 | 282680 | 21870 | 19800 | 120250 | 21600 | 21600 | 21600 | 21600 | 121600 | 77000 | 7200 | 7200 | 9000 | 175000
| Actual | 282680 | 282680 | 0 | 282680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Difference | 647390 | 228790 | 0 | 2070 | 21870 | 19800 | 120250 | 21600 | 21600 | 21600 | 21600 | 121600 | 77000 | 7200 | 7200 | 9000 | 175000
|  | Variance Percentage |  |  | 0.727% | 0% | 0% | 0% | 0% | 0% | 0% | Forecast | 21.6% | 54% | Forecast | Forecast | 5.504% | 0%
Account | Orig Budget | Current Budget | Difference
Hardware | 200000 | 125000 | 75000
Software | 300000 | 300000 | 0
Contract Service | 250000 | 325000 | -75000
Internal Labor | 250000 | 250000 | 0
TOTALS | 1000000 | 1000000 | 0

## Operating Expense
Copyright © 2020 Dan Rivera, PMP. All Rights Reserved
Account | Budget | Total Budget | YTD Budget | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01
Hardware | Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Difference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software | Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Difference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Internal Labor | Budget | 132300 | 57500 | 12800 | 9750 | 7800 | 7800 | 9750 | 3200 | 3200 | 3200 | 3200 | 6400 | 8000 | 17600 | 17600 | 22000 | 0
| Actual | 12800 | 12800 | 12800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Difference | 119500 | 44700 | 0 | 9750 | 7800 | 7800 | 9750 | 3200 | 3200 | 3200 | 3200 | 6400 | 8000 | 17600 | 17600 | 22000 | 0
Contract Service | Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Difference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Time and Expense | Budget | 20000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
| Actual | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Difference | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
OpEx Totals | Budget | 152300 | 67500 | 22800 | 9750 | 7800 | 7800 | 9750 | 3200 | 3200 | 3200 | 3200 | 6400 | 8000 | 17600 | 17600 | 22000 | 10000
| Actual | 22800 | 22800 | 22800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Difference | 129500 | 44700 | 0 | 9750 | 7800 | 7800 | 9750 | 3200 | 3200 | 3200 | 3200 | 6400 | 8000 | 17600 | 17600 | 22000 | 10000
Original Budget | Total | 2020 | 2021 | 2020-05-01: Budget Plan; 2020-06-01: Difference
Hardware | 0 | 0 | 0 | 2020-05-01: 0; 2020-06-01: 0
Software | 3000 | 0 | 0 | 2020-05-01: 0; 2020-06-01: 3000
Contract Service | 20000 | 0 | 0 | 2020-05-01: 0; 2020-06-01: 20000
Internal Labor | 100000 | 50000 | 50000 | 2020-05-01: 132300; 2020-06-01: -32300
Time and Expense | 20000 | 10000 | 10000 | 2020-05-01: 20000; 2020-06-01: 0
Cap Ex Totals | 183000 | 60000 | 70000 | 2020-05-01: 152300; 2020-06-01: -9300

## Internal Labor Dashboard
Copyright © 2020 Dan Rivera, PMP. All Rights Reserved
Project: | PMO Automation
Timeframe: | Jun, 2020
Resource | Account | Hours | Amount
Daniel Rivera | Operating | 22 | 1760
Rob Jones | Operating | 36 | 2520
OPERATING TOTALS |  | 58 | 4280
John Roberts | Capital | 180 | 16200
Ludvig Luger | Capital | 25 | 1125
Lex Borga | Capital | 25 | 1125
Jake Studd | Capital | 94 | 4230
CAPITAL TOTALS |  | 324 | 22680
Notes:
At the end of the month, make sure hours and amount match up with budgeted hours for month. Compare with budget plan.
It's okay if hours are different as you want EXACT effort.
If it's early in the month, the hours will obviously be low.
Make sure resources are booking time!
Overbooking? Why are they working so much? Will schedule be impacted?

## PO Receipt
Copyright © 2020 Dan Rivera, PMP. All Rights Reserved
PO Number | PO Line Item | Project | Vendor | PO Line Description | Purchase Order | PO to Process | Month to Process | PO to Bill | Invoices Received | Finance Rep
PO0022347 | 00010 | PMO Automation | PMO Tools, Inc. | Project Kick-Off | 50000 | 50000 | Jun, 2020 | 0 | 50000 | Daniel Rivera
PO0022347 | 00020 | PMO Automation | PMO Tools, Inc. | Software License | 150000 | 150000 | Jun, 2020 | 0 | 150000 | Daniel Rivera
PO0022347 | 00030 | PMO Automation | PMO Tools, Inc. | Requirements Signoff | 100000 | 0 | Sep, 2020 | 100000 | 0 | Daniel Rivera
PO0022347 | 00040 | PMO Automation | PMO Tools, Inc. | Development/Unit Testing | 100000 | 0 | Feb, 2021 | 100000 | 0 | Daniel Rivera
PO0022347 | 00050 | PMO Automation | PMO Tools, Inc. | User Testing / Defect Repair | 50000 | 0 | Mar, 2021 | 50000 | 0 | Daniel Rivera
PO0022347 | 00060 | PMO Automation | PMO Tools, Inc. | Production Rollout / User Training | 25000 | 0 | Jul, 2021 | 25000 | 0 | Daniel Rivera
Notes:
For each SOW, one master PO
For each deliverable, a unique PO
Line Description should match SOW milestones
PO is overall amount for deliverable
PO to process may be a fractional amount depending on work done
Month to Process is the fiscal month
PO to Bill is remaining PO to process
Invoices - makes sure that invoices are received. You can also dispute invoices if work is not done yet.
Finance Rep is the procurement or Finance person who can help you with questions.

## Original Budget
Copyright © 2020 Dan Rivera, PMP. All Rights Reserved
Project Investment | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | TOTALS
Capital
Hardware Purchase | 100000 | 100000 |  |  |  |  | 200000
Software Purchase | 100000 | 100000 |  |  |  |  | 200000
Software License | 50000 | 50000 |  |  |  |  | 100000
Vendor Expense | 125000 | 125000 |  |  |  |  | 250000
Internal Expense | 125000 | 125000 |  |  |  |  | 250000
Total Capital Expense | 500000 | 500000 | 0 | 0 | 0 |  | 1000000
Operating
Software License |  |  | 1000 | 1000 | 1000 |  | 3000
Internal Expense | 50000 | 50000 |  |  |  |  | 100000
Operate & Maintain | 0 | 0 | 10000 | 10000 |  |  | 20000
Time & Expense | 10000 | 10000 |  |  |  |  | 20000
Depreciation | 0 | 10000 | 10000 | 10000 | 10000 | 0 | 40000
Asset Write-Off | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
Total Operating Expense | 60000 | 70000 | 21000 | 21000 | 11000 |  | 183000
TOTAL INVESTMENT | 560000 | 570000 | 21000 | 21000 | 11000 |  | 1183000